## Title Page
Project Title: CST247 Minesweeper MVC ASP Application Release #: 1.3 Sprint #: 3
CST-247 : Enterprise Applications Programming III
1. Kurt Newcomb
2. Isaac Tucker
2020-12-06

## SprintProductLog
Project Title: CST247 Minesweeper MVC ASP Application
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
1 | Login Page |  | User | Login form with encryption | User info is secure | High | 2020-11-14
2 | Registration Page |  | User | User Registratin form | New users saved to database | High | 2020-11-14
3 | Login Handler |  | Developer | User input validation | Check database for user info | High | 2020-11-14
4 | Registration Handler |  | Developer | User info submission | Check if user info exists | High | 2020-11-14
5 | Database |  | Developer | Database creation for user and gameboard | Users and Game Scores separate | High | 2020-11-14
6 | Database Handler |  | Developer | Handler for users and game scores | Determine where to place data | High | 2020-11-14
7 | Game Board |  | User | GUI of Gameboard | Layout of the Gameboard | Med | 2020-11-21
8 | Leader Board(Per Difficulty) |  | User | GUI of leaders in database | List if Highest point leaders in the database | Med | 2020-12-05
9 | Store User/Gameplay Stats |  | User | I would like to way to track my information and past gameplay data | So that I can view it over time. | Med | 2020-11-14
10 | View Gameplay Stats |  | User | I would like to be able to view my past game statistics | So that I can rank myself against others | Low | 2020-11-14
11 | Play the Game |  | User | I would like to be able to play the Minesweeper Game | So i can be entertained | High | 2020-11-21
12 | Set Page Layout |  | Developer | I would like the game in a central panel and user information in a different panel | So that users can play the same and edit their informationon the same "page" | Med | 2020-11-21
13 | Set Difficulty |  | Developer | Create different variations of difficulty for gameplay | Users can experience challenging gameplay | Low
14 | Restrict to users |  | Developer | The minesweeper game to only be visisble to those logged in | So that only those with intended access can access | low
15 | Add User Info in Header |  | Developer | The user name to be on the header and for login to change to logout | For aesthetics | low
16 | GameBoard Layout |  | Developer | The gamebaord to have a layout that includes Top SCoreboard, Gameboard and User Stats | User can view his stats against top scores | low | 2020-12-05
17 | GUI |  | Developer | Update the CSS so the gameboard looks like traditional minesweeper | For nostalgia | low
18 | Game Save / DB Retrieval |  | Developer | Add the functionality for the game state to be saved to the database and loaded back later. | A player can continue a game later if they don't have time to at the moment/It's a requirement | low
19 | User Landing Page |  | Developer | Give the user a page to access all of the game functions besides playing the game | So the user has access scoreboard, save/load games, or starting a new game | low | 2020-12-05
20 | Update the GUI to partial pages |  | Developer | Update the gaeboard without refreshing the page | To save of the number of refreshes | high | 2020-12-05

## SprintBackLog
Project Title: CST247 Minesweeper MVC ASP Application Release #: 1.3 Sprint #: 3
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
8 | Leader Board(Per Difficulty) | User | GUI of leaders in database | List if Highest point leaders in the database | 4 | Kurt
16 | GameBoard Layout | Developer | The gamebaord to have a layout that includes Top SCoreboard, Gameboard and User Stats | User can view his stats against top scores | 4 | Kurt
19 | User Landing Page | Developer | Give the user a page to access all of the game functions besides playing the game | So the user has access scoreboard, save/load games, or starting a new game | 10 | Kurt and Isaac
20 | Update the GUI to partial pages | Developer | Update the gaeboard without refreshing the page | To save of the number of refreshes | 4 | Isaac

## Burn Down Chart
Project Title: CST247 Minesweeper MVC ASP Application Release #: 1.3 Sprint #: 3 | [10 empty] | Total Days: | 7
User Stories
| ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Remaining
| 8 | Leader Board(Per Difficulty) | GUI of leaders in database | Kurt | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
| 16 | GameBoard Layout | The gamebaord to have a layout that includes Top SCoreboard, Gameboard and User Stats | Kurt | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
| 19 | User Landing Page | Give the user a page to access all of the game functions besides playing the game | Kurt and Isaac | 10 | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 0
| 20 | Update the GUI to partial pages | Update the gaeboard without refreshing the page | Isaac | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 22 | 18.8571 | 15.7143 | 12.5714 | 9.4286 | 6.2857 | 3.1429 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 22 | 22 | 18 | 18 | 18 | 18 | 4 | 0

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time