## Title Page
Project Title: CST247 Minesweeper MVC ASP Application Release #: 1.4 Sprint #: 4
CST-247 : Enterprise Applications Programming III
1. Kurt Newcomb
2. Isaac Tucker
2020-12-12

## SprintProductLog
Project Title: CST247 Minesweeper MVC ASP Application
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
1 | Login Page |  | User | Login form with encryption | User info is secure | High | 2020-11-14
2 | Registration Page |  | User | User Registratin form | New users saved to database | High | 2020-11-14
3 | Login Handler |  | Developer | User input validation | Check database for user info | High | 2020-11-14
4 | Registration Handler |  | Developer | User info submission | Check if user info exists | High | 2020-11-14
5 | Database |  | Developer | Database creation for user and gameboard | Users and Game Scores separate | High | 2020-11-14
6 | Database Handler |  | Developer | Handler for users and game scores | Determine where to place data | High | 2020-11-14
7 | Game Board |  | User | GUI of Gameboard | Layout of the Gameboard | Med | 2020-11-21
8 | Leader Board(Per Difficulty) |  | User | GUI of leaders in database | List if Highest point leaders in the database | Med | 2020-12-05
9 | Store User/Gameplay Stats |  | User | I would like to way to track my information and past gameplay data | So that I can view it over time. | Med | 2020-11-14
10 | View Gameplay Stats |  | User | I would like to be able to view my past game statistics | So that I can rank myself against others | Low | 2020-11-14
11 | Play the Game |  | User | I would like to be able to play the Minesweeper Game | So i can be entertained | High | 2020-11-21
12 | Set Page Layout |  | Developer | I would like the game in a central panel and user information in a different panel | So that users can play the same and edit their informationon the same "page" | Med | 2020-11-21
13 | Set Difficulty |  | Developer | Create different variations of difficulty for gameplay | Users can experience challenging gameplay | Low
14 | Restrict to users |  | Developer | The minesweeper game to only be visisble to those logged in | So that only those with intended access can access | low | 2020-12-12
15 | Add User Info in Header |  | Developer | The user name to be on the header and for login to change to logout | For aesthetics | low | 2020-12-12
16 | GameBoard Layout |  | Developer | The gamebaord to have a layout that includes Top SCoreboard, Gameboard and User Stats | User can view his stats against top scores | low | 2020-12-05
17 | GUI |  | Developer | Update the CSS so the gameboard looks like traditional minesweeper | For nostalgia | low
18 | Game Save / DB Retrieval |  | Developer | Add the functionality for the game state to be saved to the database and loaded back later. | A player can continue a game later if they don't have time to at the moment/It's a requirement | low | 2020-12-12
19 | User Landing Page |  | Developer | Give the user a page to access all of the game functions besides playing the game | So the user has access scoreboard, save/load games, or starting a new game | low | 2020-12-05
20 | Update the GUI to partial pages |  | Developer | Update the gaeboard without refreshing the page | To save of the number of refreshes | high | 2020-12-05
21 | Add REST for scores |  | Developer | Make game scores accessible via REST | So that other applications can retrieve if needed. | High | 2020-12-12

## SprintBackLog
Project Title: CST247 Minesweeper MVC ASP Application Release #: 1.4 Sprint #: 4
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
14 | Restrict to users | Developer | The minesweeper game to only be visisble to those logged in | So that only those with intended access can access | 4 | Isaac
15 | Add User Info in Header | Developer | The user name to be on the header and for login to change to logout | For aesthetics | 4 | Isaac
18 | Game Save / DB Retrieval | Developer | Add the functionality for the game state to be saved to the database and loaded back later. | A player can continue a game later if they don't have time to at the moment/It's a requirement | 10 | Isaac
21 | Add REST for scores | Developer | Make game scores accessible via REST | So that other applications can retrieve if needed. | 10 | Kurt

## Burn Down Chart
Project Title: CST247 Minesweeper MVC ASP Application Release #: 1.4 Sprint #: 4 | [10 empty] | Total Days: | 7
User Stories
| ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Remaining
| 14 | Restrict to users | Make game only accesible to logged in users | Isaac | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| 15 | Add User Info in Header | Update header so Login and Reigster change once someone is logged in | Isaac | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| 18 | Game Save / DB Retrieval | Make it so user's can save their gamestate and load from last save (if not win/lose) when they return. | Isaac | 10 | 0 | 0 | 0 | 4 | 4 | 2 | 0 | 0
| 21 | Add REST for scores | Provide REST services so that game scores can be retrieved. | Kurt | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 28 | 28 | 28 | 20 | 16 | 12 | 2 | 0