## Title Page
Project Title: CST247 Minesweeper MVC ASP Application Release #: 1.1 Sprint #: 1
CST-247 : Enterprise Applications Programming III
1. Kurt Newcomb
2. Isaac Tucker
2020-11-14

## SprintProductLog
Project Title: CST247 Minesweeper MVC ASP Application Release #: 1.1 Sprint #: 1
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
1 | Login Page |  | User | Login form with encryption | User info is secure | High | 2020-11-14
2 | Registration Page |  | User | User Registratin form | New users saved to database | High | 2020-11-14
3 | Login Handler |  | Developer | User input validation | Check database for user info | High | 2020-11-14
4 | Registration Handler |  | Developer | User info submission | Check if user info exists | High | 2020-11-14
5 | Database |  | Developer | Database creation for user and gameboard | Users and Game Scores separate | High | 2020-11-14
6 | Database Handler |  | Developer | Handler for users and game scores | Determine where to place data | High | 2020-11-14
7 | Game Board |  | User | GUI of Gameboard | Layout of the Gameboard | Med
8 | Leader Board(Per Difficulty) |  | User | GUI of leaders in database | List if Highest point leaders in the database | Med
9 | Store User/Gameplay Stats |  | User | I would like to way to track my information and past gameplay data | So that I can view it over time. | Med | 2020-11-14
10 | View Gameplay Stats |  | User | I would like to be able to view my past game statistics | So that I can rank myself against others | Low | 2020-11-14
11 | Play the Game |  | User | I would like to be able to play the Minesweeper Game | So i can be entertained | High
12 | Set Page Layout |  | Developer | I would like the game in a central panel and user information in a different panel | So that users can play the same and edit their informationon the same "page" | Med
13 | Set Difficulty |  | Developer | Create different variations of difficulty for gameplay | Users can experience challenging gameplay | Low

## SprintBackLog
Project Title: CST247 Minesweeper MVC ASP Application Release #: 1.1 Sprint #: 1
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
9 | Store User/Gameplay Stats | User | I would like to way to track my information and past gameplay data | So that I can view it over time. | 1 | Isaac T
10 | View Gameplay Stats | User | I would like to be able to view my past game statistics | So that I can rank myself against others | 1 | Isaac T
1 | Login Page | User | Login form with encryption | User info is secure | 1 | Isaac T
2 | Registration Page | User | User Registratin form | New users saved to database | 1 | Kurt N
3 | Login Handler | Developer | User input validation | Check database for user info | 1 | Isaac T
4 | Registration Handler | Developer | User info submission | Check if user info exists | 1 | Kurt N
5 | Database | Developer | Database creation for user and gameboard | Users and Game Scores separate | 4 | Isaac T / Kurt N
6 | Database Handler | Developer | Handler for users and game scores | Determine where to place data | 4 | Isaac T / Kurt N

## Burn Down Chart
Project Title: CST247 Minesweeper MVC ASP Application Release #: 1.1 Sprint #: 1 | [10 empty] | Total Days: | 7
User Stories
| ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Remaining
| 9 | As a User I would like to way to track my information and past gameplay data. | (IDs: 9) Create User Model | Team Member | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | (IDs: 5) Create Database and User table | Team Member | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0
|  |  | (IDs: 6) Create business data service and data service to communicate with database | Team Member | 4 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 0
|  |  | (IDs: 1,2,3,4)Create Register/Login feature to store/retrieve user data | Team Member | 4 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 0
| 10 | As a User I would like to be able to view my past game statistics | (IDs: 10) Create view to display user gameplay stats | Team Member | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 9 | 7 | 7 | 7 | 7 | 1 | 1

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time